## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
Personnel | Loss team members | One or more team members drop the class | 1 | 4 | 4 | 40 | team leader and all members | 2025-10-20 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members | add new team members | 1 | 3 | 3 | 45 | team leader and all members | 2025-10-20 | Redistribute tasks. | Zixuan was added after the initial composition of the team. He's been integrated and collaborating. | Open
| Lack of motivation or responsibility | Lack of motivation or responsibility | 1 | 5 | 5 | 25 | team leader and all members | 2025-10-20 | Talk to see what's going on and see if others can help | Nothing so far (phew!) | Open
Communication | Ineffective communication - lack of clarity of individual goals | If individual goals/tasks are not clear, time will be wasted in unnecesary work that will not add to the project | 1 | 3 | 4 | 60 | team leader and all members | 2025-10-20 | Talk to see what's going on and see if others can help | Nothing so far (phew!) | Open
| Duplicative work because of miscommunication |  | 3 | 1 | 1 | 1 | team leader and all members | 2025-10-20 | Improve communication. Notify others via discord when a pull request has been issued. | There was a minor miscommunication instance where two team members worked on the same item without the other knowing. | Open
Requirements | unclear requirements | unclear requirements | 2 | 3 | 3 | 36 | team leader and all members | 2025-10-20 | Talk to see what's going on and see if others can help | Nothing so far (phew!) | Open
| scope creep |  | 2 | 3 | 3 | 36 | team leader and all members | 2025-10-20 | Meet with the team to discuss and redefine the scope and set more defined, manageable goals. | The team realized the goals set for iteration 1 were too ambitious for the available timeframe, and decided to meet to redefine the scope for this iteration. Setting more manageable goals allowed the team to complete high quality work and make significant progress while meeting the deadline. | Open
Management | lack of management skills | lack of management skills | 3 | 5 | 5 | 15 | team leader and all members | 2025-10-20 | Increase communication to ensure all parties are aligned. | Team Leader needs to ensure assigned tasks are fully communicatted and understood by asignees before starting actual work. | Open
Technology competence | Not familiar with the framework used |  | 2 | 3 | 3 | 36 | team leader and all members | 2025-10-20 | Talk to see what's going on and see if others can help | Nothing so far (phew!) | Open
| Other technology incompetence |  | 2 | 3 | 3 | 36 | team leader and all members | 2025-10-20 | Conduct further research and experiments to determine suitability. | Assumed that Google Cloud Run would be easier to work with and a good fit for this project. Turned out not to be the case, pivot to AWS. | Open
Design and implementation | Improper design |  | 2 | 5 | 5 | 20 | team leader and all members | 2025-10-20 | Improve communication. Notify others via discord when a pull request has been issued. | Slightly different external API service signatures were implemented, not allowing for a common interface. | Open
| Messy code |  | 2 | 3 | 4 | 48 | team leader and all members | 2025-10-20 | Talk to see what's going on and see if others can help | Nothing so far (phew!) | Open
Testing | Not enough testing |  | 2 | 4 | 4 | 32 | team leader and all members | 2025-10-20 | Talk to see what's going on and see if others can help | Nothing so far (phew!) | Open
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.