## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
Personnel | Loss team members | One or more team members drop the class | 1 | 4 | 4 | 40 | team leader and all members | 2025-10-20 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members | add new team members | 1 | 3 | 3 | 45 | team leader and all members | 2025-10-20 | Redistribute tasks. | No one added so far. | Open
| Lack of motivation or responsibility | Lack of motivation or responsibility | 1 | 5 | 5 | 25 | team leader and all members | 2025-10-20 | Talk to see what's going on and see if others can help | Nothing so far (phew!) | Open
Communication | Ineffective communication - lack of clarity of individual goals | If individual goals/tasks are not clear, time will be wasted in unnecesary work that will not add to the project | 1 | 3 | 4 | 60 | team leader and all members | 2025-10-20 | Talk to see what's going on and see if others can help | Nothing so far (phew!) | Open
Requirements | unclear requirements | unclear requirements | 2 | 3 | 3 | 36 | team leader and all members | 2025-10-20 | Talk to see what's going on and see if others can help | Nothing so far (phew!) | Open
| scope creep |  | 2 | 3 | 3 | 36 | team leader and all members | 2025-10-20 | Talk to see what's going on and see if others can help | Nothing so far (phew!) | Open
Management | lack of management skills | lack of management skills | 3 | 5 | 5 | 15 | team leader and all members | 2025-10-20 | Talk to see what's going on and see if others can help | Nothing so far (phew!) | Open
Technology competence | Not familiar with the framework used |  | 2 | 3 | 3 | 36 | team leader and all members | 2025-10-20 | Talk to see what's going on and see if others can help | Nothing so far (phew!) | Open
| Other technology incompetence |  | 2 | 3 | 3 | 36 | team leader and all members | 2025-10-20 | Talk to see what's going on and see if others can help | Nothing so far (phew!) | Open
Design and implementation | Improper design |  | 2 | 5 | 5 | 20 | team leader and all members | 2025-10-20 | Talk to see what's going on and see if others can help | Nothing so far (phew!) | Open
| Messy code |  | 2 | 3 | 4 | 48 | team leader and all members | 2025-10-20 | Talk to see what's going on and see if others can help | Nothing so far (phew!) | Open
Testing | Not enough testing |  | 2 | 4 | 4 | 32 | team leader and all members | 2025-10-20 | Talk to see what's going on and see if others can help | Nothing so far (phew!) | Open
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.