## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 09/03-09/10 | - Team composition - Team meeting. - Team role definition - Project selection - High level requirement definition - Tech stack discussion and determination - Github teams and repo creation. - Github lab1 branch creation | Minor issues setting up SSH keys for github repo. | None | - Continue setting up the environment. Next step will be setting up CI/CD pipeline. - Setting up Jira - Refine requirements - Come up with first architectural design | [5 empty] | 43.5 |  | 2 | 16 | 6 | 3.5 | 0 | 0 | 13 | 5
1
2
3

## Edoardo Cavallero
Your Lead Roles: Design and Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/03-09/10 | 9.5 | 7 | 2.5 | 0 - learned more about git, django, OAuth, FastAPI through online and AI research 2 - researched database solutions 5 - used Discord and Google Meet to communicate with the team and join meetings, drafted management plan timeilne 6 - cloned and set up Git to manage project repo, joined class organization and team on GitHub, created README file and committed to project repository 7 - prepared group presentation, created application logo | 1 |  | 0.5 |  |  | 2 | 1 | 2.5 | - Used ChatGPT to format and organize risk management paragraph and design application logo. The output was helpful. I suggested some slight editing after the first formatting. Content of paragraph was original work so I just fine tuned the formatting to preserve more of the original details. Logo design was well made after first prompt | - Wrote two sections of SPPP (Risk management and management plan timeline) - Created Google Slides document for team presentation - Created application logo - Updated progress report - Helped ensure correct github configuration - Created and committed project README file | - struggled to identify full set of deliverables and keep track of all documents to be submitted | - communicate with instructor to find effective ways to track deliverables each week, asked for complete list of assignments on BlackBoard | - continue to learn about selected tech stack - continue researching free cloud based db solutions - refine project architecture and plans for front end/back end split - plan team meetings - contribute to iteration 1 and team presentation - update progress report | 2025-08-10

## Michael Laszlo
Your Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/03-09/10 | 7.5 | 5.5 | 2 | 0 - Research python FastAPI, 1 - Investigate Security Considerations for FastAPI, 5 - Used the Discord and Google Meetings to meet the team as well as decide the project, 6 - Setup SSH keys on my laptop so I can easily use Git with the team repo | 2 | 1 |  |  |  | 2 | 0.5 |  | Used Chat-GPT to help me investigate non-functional requirements that a Security Leader should consider, especially as it pertains to FastAPI. This was useful because it help me get an idea of the aspects I should be monitoring and considering throughout the project to ensure the team is maintaining best security practices. I used the results to help shape the security requirements and some feature requirements of the project. Using Chat-GPT was useful here because it brought up ideas I had not considered that I then incorporated into our non-functional requirements to help the team develop a more secure application. | 1. Write Security Requirements section of SPPP and added some feature requirements as Security Leader 2. Set up git and committed initial team.md file 3. Participate in team kickoff meeting. 4. Presented half of Iteration 0 presentation | 1. Not familiar with FastAPI 2. Project design not decided or discussed yet, hard to plan tasks | 1. Finish FastAPI starter project from documentation this weekend to get some exposure 2. Meet with team to discuss project design and align on task direction | 0 - Continue to learn FastAPI & Python security best practices 1 - continue to define requirements 3 - Implement a basic FastAPI project to get myself acquainted with the framework 5 - Meet with team to discuss project in more depth and continue designing architecture | 6

## Zixuan Cheng
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/03-09/10 | 5.5 | 4.5 | 1 | 0 - learn git and fastapi 1 - define high level requirements 2 - design 3 - implementation 4 - test 5 - keep touch with team members 6 - set up git and commit lab1 7 - unclassified | 2 | 1 | 0.5 | 0 | 0 | 0.5 | 0.5 | 0 | 1.Use ChatGPT to research the role of the Design and Implementation Leader. 2.Use ChatGPT to research possible tech stacks for our project, including options for the front-end, back-end, database, and cloud deployment. 3.Use DeepSeek to help me summarize the Objectives and Priorities section, and check for typos or errors in the summary. | 1. Write half sections of SPPP. 2. Set up git. 3.Research the tech stack of out project. | 1. not familiar with team members and missed first meeting. 2. have no experience in python web development. 3. not familiar with fastapi. | 1. Learning fastapi from tutorials and chatgpt. 2. Try to make a demo using fastapi | 0 - continue to learn fastapi. 1 - make a demo using fastapi. 3 - implement a basic hello world on fastapi. | 6

## Zhehao Liao
Your Lead Roles: Requirement Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/03-09/10 | 9 | 7 | 2 | 0 - explored requirement practices for similar products 1 - defined core functional needs of our products 2 - design 3 - implementation 4 - test 5 - communicated with teammates about requirements 6 - set up git 7 - prepared presentation | 3 | 2 | 0.5 | 0 | 0 | 0.5 | 0.5 | 0.5 | Used ChatGPT to help brainstorm more possible requirements and filter unrealistic ones. | 1. Wrote functional requirement sections of SPPP 2. Set up git, renewed and committed files on git 3. Updated the progress report 4. Worked on Iteration 4 Presentation | The current requirements are still high-level and not detailed enough, making it difficult to start design discussions. | I will work on breaking down the requirements into smaller user stories and organize them by priority, so the design team can start with clear guidance. | 0 – studied techniques for creating requirement traceability matrices to connect requirements with later design and testing. 1 – transformed high-level requirements of Concert Finder into detailed use cases and acceptance criteria. 5 – discussed with teammates to confirm feature priorities and requirements with the upcoming design tasks. | 10

## Samuel Akerman
Your Lead Roles: Team Leader, Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/03-09/10 | 7 | 5 | 2 | 0 - investigated different python libraries we can leverage. 1 - define high level requirements, 2 - Design 3 - Implementation 4 - Test 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 5 | 2 | 2 | 0 | 0 | 5 | 2 | 3 | Used ChatGPT to branstorm possible project ideas, given my interests. Also used it to come of with potential nice names for our project. | 1. Wrote 3 sections of SPPP 2. Wrote meeting 1 minute. 3. Wrote risks spreadsheet. 4. Updated progress report. 6. Worked on iteration 0 presentation 5. Set up git, created lab1 branch. | 1. Found challenging to understand exactly what all the deliverables were. 2. Ensure all members of the team know what they should be working on. | 1. Ask questions. Make sure to read chat as others have had similar questions. 2. Inventory pending tasks and communicate. Will start using Jira. | 0 - Setup CICD pipeline 1 - Setup Docker 3 - Start experimenting with APIs to find and process concert data | 10

## Greg Grimaylo
Your Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/03-09/10 | 9 | 7 | 2 | 0 - researched Python libraries/frameworks we can use to test our code like FastAPI, metrics we can use to measure our product effectively 5 - made project QA plan 6 - set up git, github, vscode 7 - research similar feature in Spotify, prepare presentation | 3 |  |  |  |  | 3 | 0.5 | 0.5 | Use chatgpt to research QA testing plan for our product. It was helpful in suggesting metrics we could use to measure the quality of our software, and frameworks/tools we could use to test our code. I filtered the results based on how useful I thought they would be to our product and also by how feasible it was to use the suggestion provided by chatgpt | 1. Write QA plan section of SPPP 2. Set up git, commit a test message on git 3. Contribute to Iteration 0 presentation 4. Contributed to Risk Management document | 1. not familar with using Docker or containerization in general 2. have not worked with Python in a while, need a refresher. | 1. learn about containerization and work on Lab 2 which deals with Docker 2. refresh memory on Python | 0 - learn Docker, practice with Python 4 - continue to define QA plan 5 - meet with team to work on Iteration 1 | 8

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments